## Sheet1
Machine Type | Machine Subtype | Milestone | Activity Type | Activity Subtype | Mandays
Packing | NEXGEN-FRP-12-12--SI-TP | Design | Design activity | Received PR sheet & Allot RPO Number (Electrical + Mechanical) | 0.1
|  |  |  | Design Release through NAV | 0.2
|  |  |  | Manual Preperation | 0.2
|  | Production | Mechanical Assembly | Base Frame Assembly | 0.5
|  |  |  | Tank mounting bracket with heater plate mounting | 0.5
|  |  |  | Electrical panel & HMI panel mounting | 0.5
|  |  |  | Metering Unit Assembly | 0.5
|  |  |  | Tank Assembly | 0.5
|  |  |  | Hose preparation | 0.5
|  |  |  | FRP Cover fitting | 0.25
|  |  |  | Safety legends & Name plate fitting | 0.25
|  |  | Electrical Assembly | Electrical layout, MP wiring, OP wiring | 2
|  |  |  | M/C wiring, I/O checking, labeling & parameter setting | 2
|  |  | Software Assembly | Machine PLC programing | 0.25
|  | Purchase | Reciept of Bought out items | Reciept of Bought out items | 56
|  |  | Reciept of Manufacturing items | Reciept of Manufacturing items | 21
|  | Testing | Internal machine trials | Internal machine trials ( Vacu.leak test,Temp. trial, ratio trials, Mixing trial,hardness report,etc) | 2
|  |  | Quality checking | Quality checking | 0.5
|  | Dispatch | Machine cleaning & dispatch activities | Machine cleaning & dispatch activities | 0.25
Packing | NEXGEN-FRP-12-12---SI-KTP | Design | Design activity | Received PR sheet & Allot RPO Number (Electrical + Mechanical) | 0.1
|  |  |  | Design Release through NAV | 0.2
|  |  |  | Manual Preperation | 0.2
|  | Production | Mechanical Assembly | Base Frame Assembly | 0.5
|  |  |  | Tank mounting bracket with heater plate mounting | 0.5
|  |  |  | Electrical panel & HMI panel mounting | 0.5
|  |  |  | Metering Unit Assembly | 0.5
|  |  |  | Tank Assembly | 0.5
|  |  |  | Hose preparation | 0.5
|  |  |  | FRP Cover fitting | 0.25
|  |  |  | Safety legends & Name plate fitting | 0.25
|  |  | Electrical Assembly | Electrical layout, MP wiring, OP wiring | 2
|  |  |  | M/C wiring, I/O checking, labeling & parameter setting | 2
|  |  | Software Assembly | Machine PLC programming | 0.25
|  | Purchase | Reciept of Bought out items | Reciept of Bought out items | 56
|  |  | Reciept of Manufacturing items | Reciept of Manufacturing items | 21
|  | Testing | Internal machine trials | Internal machine trials ( Vacu.leak test,Temp. trial, ratio trials, Mixing trial,hardness report,etc) | 2
|  |  | Quality checking | Quality checking | 0.5
|  | Dispatch | Machine cleaning & dispatch activities | Machine cleaning & Dispatch activities | 0.25
Packing | NEXGEN-FRP-12-12-AR-H-SI-TP | Design | Design activity | Received PR sheet & Allot RPO Number (Electrical + Mechanical) | 0.1
|  |  |  | Design Release through NAV | 0.2
|  |  |  | Manual Preperation | 0.2
|  | Production | Mechanical Assembly | Base Frame Assembly | 0.5
|  |  |  | Tank mounting bracket with heater plate mounting | 0.5
|  |  |  | Electrical panel & HMI panel mounting | 0.5
|  |  |  | Metering Unit Assembly | 0.5
|  |  |  | Tank Assembly | 0.5
|  |  |  | Hose preparation | 0.5
|  |  |  | FRP Cover fitting | 0.25
|  |  |  | Autorefilling assembly | 0.25
|  |  |  | Safety legends & Name plate fitting | 0.25
|  |  | Electrical Assembly | Electrical layout, MP wiring, OP wiring | 2
|  |  |  | M/C wiring, I/O checking, labeling & parameter setting | 2
|  |  | Software Assembly | Machine PLC programming | 0.25
|  | Purchase | Reciept of Bought out items | Reciept of Bought out items | 56
|  |  | Reciept of Manufacturing items | Reciept of Manufacturing items | 21
|  | Testing | Internal machine trials | Internal machine trials ( Vacu.leak test,Temp. trial, ratio trials, Mixing trial,hardness report,etc) | 2
|  |  | Quality checking | Quality checking | 0.5
|  | Dispatch | Machine cleaning & dispatch activities | Machine cleaning & Dispatch activities | 0.25
MMD | INTELLO-ET-1.5 -3.6-GR45-100-10-I-1H-DM | Design | Design activity | Study of PR sheet/ RFQ | 1
|  |  |  | Understanding machine requirement | 1
|  |  |  | Preperation of DAP document + Machine calculations | 3
|  |  |  | DAP Submission + coordination/ customer meeting/ DAP visit | 0.5
|  |  |  | Customer Approval (Optionl, Max days considered) | 7
|  |  |  | Long Lead release | 1
|  |  |  | Updation on DAP points and detail designing/drafting | 2
|  |  |  | Design Release through NAV | 1
|  |  |  | Release of testing chart whenever required. | 1
|  |  |  | Design Support during on shopfloor | 0.5
|  |  |  | MOM point clearance as per PDI | 1
|  |  |  | Manual Preperation | 2
|  | Production | Mechanical Assembly | Base frame assembly | 0.5
|  |  |  | Melter assembly | 2
|  |  |  | Electical panel cutout & mounting | 1
|  |  |  | Tank assembly | 2
|  |  |  | Stirrer assembly | 1
|  |  |  | Metering unit assembly | 2
|  |  |  | FRL & SV mounting with extrusion frame assembly | 1.5
|  |  |  | Vacuum line assembly | 2
|  |  |  | Mixer assembly | 2
|  |  |  | Hose preparation | 1
|  |  |  | Ducting & pneumatic tubing | 2
|  |  |  | Flushing tank assembly | 0.5
|  |  |  | Legends, name plate, safety stickers,arrows | 0.5
|  |  | Electrical Assembly | Electrical layout, MP wiring, OP wiring | 6
|  |  |  | M/C wiring, I/O checking, labeling & parameter setting | 6
|  |  | Software Assembly | Machine PLC programming | 1
|  | Purchase | Reciept of Bought out items | Reciept of Bought out items | 56
|  |  | Reciept of Manufacturing items | Reciept of Manufacturing items | 21
|  | Testing | Internal machine trials | Internal machine trials ( Vacu.leak test,Temp. trial, ratio trials, Mixing trial,hardness report,etc) | 8
|  |  | Quality checking | Quality checking | 1
|  |  | Customer PDI | Customer PDI | 4
|  | Dispatch | Machine cleaning & dispatch activities | MOM completion | 2
|  |  |  | Machine cleaning & Dispatch activities | 6
MMD | INTELLO-ET- 2-8-MOCA-200-45-I-S-1H-DM | Design | Design activity | Study of PR sheet/ RFQ | 1
|  |  |  | Understanding machine requirement | 1
|  |  |  | Preperation of DAP document + Machine calculations | 3
|  |  |  | DAP Submission + coordination/ customer meeting/ DAP visit | 0.5
|  |  |  | Customer Approval (Max) | 7
|  |  |  | Long Lead release | 1
|  |  |  | Updation on DAP points and detail designing/drafting | 2
|  |  |  | Design Release through NAV | 1
|  |  |  | Release of testing chart whenever required. | 1
|  |  |  | Design Support during on shopfloor | 0.5
|  |  |  | MOM point clearance as per PDI | 1
|  |  |  | Manual Preperation | 2
|  | Production | Mechanical Assembly | Base frame assembly | 0.5
|  |  |  | Melter assembly | 2
|  |  |  | Electical panel cutout & mounting | 1
|  |  |  | Tank assembly | 2
|  |  |  | Stirrer assembly | 1
|  |  |  | Metering unit assembly | 2
|  |  |  | FRL & SV mounting with extrusion frame assembly | 1.5
|  |  |  | Vacuum line assembly | 2
|  |  |  | Mixer assembly | 2
|  |  |  | Hose preparation | 1
|  |  |  | Ducting & pneumatic tubing | 2
|  |  |  | Flushing tank assembly | 0.5
|  |  |  | Legends, name plate, safety stickers,arrows | 0.5
|  |  | Electrical Assembly | Electrical layout, MP wiring, OP wiring | 6
|  |  |  | M/C wiring, I/O checking, labeling & parameter setting | 6
|  |  | Software Assembly | Machine PLC programming | 1
|  | Purchase | Reciept of Bought out items | Reciept of Bought out items | 56
|  |  | Reciept of Manufacturing items | Reciept of Manufacturing items | 21
|  | Testing | Internal machine trials | Internal machine trials ( Vacu.leak test,Temp. trial, ratio trials, Mixing trial,hardness report,etc) | 8
|  |  | Quality checking | Quality checking | 1
|  |  | Customer PDI | Customer PDI | 4
|  | Dispatch | Machine cleaning & dispatch activities | MOM completion | 2
|  |  |  | Machine cleaning & Dispatch activities | 6
MMD | INTELLO-AE -0.5-1.2-GG-35SH-35SH-I-2H-SM | Design | Design activity | Study of PR sheet/ RFQ | 1
|  |  |  | Understanding machine + customer requirement | 1.5
|  |  |  | Preperation of DAP document + Machine calculations | 7
|  |  |  | DAP Submission + coordination/ customer meeting/ DAP visit | 1
|  |  |  | Customer Approval (Max) | 7
|  |  |  | Long Lead release | 2
|  |  |  | Updation on DAP points and detail designing | 4
|  |  |  | Integration of attachment modeling and Detail drafting | 5
|  |  |  | Release of documentation+ P&I + flowcharts,Process parameter sheet, etc. | 2
|  |  |  | Design Release through NAV | 0.5
|  |  |  | Design Support during PDI | 1
|  |  |  | Manual Preperation | 3
|  |  |  | MOM point clearance as per PDI | 2
|  | Production | Mechanical Assembly | MMD Base Frame Assembly | 0.5
|  |  |  | MMD Extrusion Frame Assembly | 0.5
|  |  |  | Electrical Panel Cutout & mounting | 1
|  |  |  | Tank Assembly | 2
|  |  |  | Stirrer Assembly | 1
|  |  |  | Metering Unit Assembly | 2
|  |  |  | Vacuum line Assembly | 1
|  |  |  | Pneumatic tubing & ferruling | 1
|  |  |  | FRL & SV valve mtg | 1
|  |  |  | Robotic Base frame assembly | 0.5
|  |  |  | Extrusion frame & top sheet mounting | 0.5
|  |  |  | Robotic plate & robot mounting | 0.5
|  |  |  | Base plate mounting | 0.5
|  |  |  | Hose preparation | 0.5
|  |  |  | Curtain sensor & job sensors mounting | 0.5
|  |  |  | Ducting, pneumatic tubing & ferruling | 0.5
|  |  |  | Gun Assembly (Static/Dynamic) | 1
|  |  |  | Flush panel & Acrylic fitting. | 1
|  |  |  | Legends, name plate, safety stickers, arrows | 0.5
|  |  | Electrical Assembly | Electrical layout, MP wiring, OP wiring | 6
|  |  |  | M/C wiring, I/O checking, labeling & parameter setting | 6
|  |  | Software Assembly | Robot teching & programming | 1
|  |  |  | Machine PLC programming | 1
|  | Purchase | Reciept of Bought out items | Reciept of Bought out items | 56
|  |  | Reciept of Manufacturing items | Reciept of Manufacturing items | 21
|  | Testing | Internal machine trials | Internal machine trials ( Vacu.leak test,Temp. trial, ratio trials, Mixing trial,hardness report,etc) | 7
|  |  | Quality checking | Quality checking | 1
|  |  | Customer PDI | Customer PDI | 2
|  | Dispatch | Machine cleaning & dispatch activities | MOM completion | 2
|  |  |  | Machine cleaning & Dispatch activities | 6
MMD | INTELLO-ET- 10-20-MOCA-200-200-100-I-I-S-1H-DM | Design | Design activity | Study of PR sheet/ RFQ | 1
|  |  |  | Understanding machine + customer requirement | 1.5
|  |  |  | Preperation of DAP document + Machine calculations | 7
|  |  |  | DAP Submission + coordination/ customer meeting/ DAP visit | 1
|  |  |  | Customer Approval (Max) | 7
|  |  |  | Long Lead release | 2
|  |  |  | Updation on DAP points and detail designing | 4
|  |  |  | Integration of attachment modeling and Detail drafting | 5
|  |  |  | Release of documentation+ P&I + flowcharts,Process parameter sheet, etc. | 2
|  |  |  | Design Release through NAV | 0.5
|  |  |  | Design Support during PDI | 1
|  |  |  | Manual Preperation | 3
|  |  |  | MOM point clearance as per PDI | 2
|  | Production | Mechanical Assembly | Base frame assembly | 0.5
|  |  |  | Melter assembly | 2
|  |  |  | Electical panel cutout & mounting | 1
|  |  |  | Tank assembly | 3
|  |  |  | Stirrer assembly | 1.5
|  |  |  | Metering unit assembly | 3
|  |  |  | FRL & SV mounting with extrusion frame assembly | 1
|  |  |  | Pigment metering units assembly | 1
|  |  |  | Vacuum line assembly | 2
|  |  |  | Mixer assembly | 2
|  |  |  | Hose preparation | 2
|  |  |  | Ducting & pneumatic tubing | 2
|  |  |  | Flushing tank assembly | 0.5
|  |  |  | Legends, name plate, safety stickers,arrows | 0.5
|  |  | Electrical Assembly | Electrical layout, MP wiring, OP wiring | 8
|  |  |  | M/C wiring, I/O checking, labeling & parameter setting | 14
|  |  | Software Assembly | Machine PLC programming | 1
|  | Purchase | Reciept of Bought out items | Reciept of Bought out items | 56
|  |  | Reciept of Manufacturing items | Reciept of Manufacturing items | 21
|  | Testing | Internal machine trials | Internal machine trials ( Vacu.leak test,Temp. trial, ratio trials, Mixing trial,hardness report,etc) | 8
|  |  | Quality checking | Quality checking | 1
|  |  | Customer PDI | Customer PDI | 4
|  | Dispatch | Machine cleaning & dispatch activities | MOM completion | 2
|  |  |  | Machine cleaning & Dispatch activities | 8
MMD | OPTI-AE -0.1-0.3-GG-5-5-S-1H-SM | Design | Design activity | Study of PR sheet/ RFQ | 1
|  |  |  | Understanding machine + customer requirement | 1
|  |  |  | Preperation of DAP document + Machine calculations | 2
|  |  |  | DAP Submission + coordination/ customer meeting/ DAP visit | 0.5
|  |  |  | Customer Approval (Max) | 7
|  |  |  | Long Lead release | 1
|  |  |  | Updation on DAP points and detail designing & drafting | 3
|  |  |  | Release of documentation+ P&I + flowchartsProcess parameter sheet, etc. | 2
|  |  |  | Design Release through NAV | 1
|  |  |  | Design Support during PDI | 0.5
|  |  |  | MOM point clearance as per PDI | 1
|  |  |  | Manual Preperation | 2
|  | Production | Mechanical Assembly | Base Frame Assembly | 0.5
|  |  |  | Extrusion frame | 0.5
|  |  |  | Electrical panel cutout & mounting | 1
|  |  |  | Tank Assembly | 1
|  |  |  | Stirrer Assembly | 1
|  |  |  | Metering unit Assembly with report | 1.5
|  |  |  | Vacuum line Assembly | 1
|  |  |  | Pneumatic tubing and ferruling (Ducting & FRL mtg SV mtg) | 1
|  |  |  | Boom Assembly | 0.5
|  |  |  | Gun assly (TWIN gun assly & testing report) | 0.5
|  |  |  | Hose preparation | 0.5
|  |  |  | Flushing trolley assembly | 0.5
|  |  |  | Name plate, all legends (safety), acrylic cutting. | 0.5
|  |  | Electrical Assembly | Electrical layout, MP wiring, OP wiring | 4
|  |  |  | M/C wiring, I/O checking, labeling & parameter setting | 1
|  |  | Software Assembly | Machine PLC programming | 1
|  | Purchase | Reciept of Bought out items | Reciept of Bought out items | 56
|  |  | Reciept of Manufacturing items | Reciept of Manufacturing items | 21
|  | Testing | Internal machine trials | Internal machine trials ( Vacu.leak test,Temp. trial, ratio trials, Mixing trial,hardness report,etc) | 4
|  |  | Quality checking | Quality checking | 1
|  |  | Customer PDI | Customer PDI | 2
|  | Dispatch | Machine cleaning & dispatch activities | MOM completion | 1
|  |  |  | Machine cleaning & Dispatch activities | 4
MMD | OPTI-AE -0.5-1.2-PG-5-5-I-1H-SM | Design | Design activity | Study of PR sheet/ RFQ | 1
|  |  |  | Understanding machine + customer requirement | 1
|  |  |  | Preperation of DAP document + Machine calculations | 2
|  |  |  | DAP Submission + coordination/ customer meeting/ DAP visit | 0.5
|  |  |  | Customer Approval (Max) | 7
|  |  |  | Long Lead release | 1
|  |  |  | Updation on DAP points and detail designing & drafting | 3
|  |  |  | Release of documentation+ P&I + flowchartsProcess parameter sheet, etc. | 2
|  |  |  | Design Release through NAV | 1
|  |  |  | Design Support during PDI | 0.5
|  |  |  | MOM point clearance as per PDI | 1
|  |  |  | Manual Preperation | 2
|  | Production | Mechanical Assembly | Base Frame Assembly | 0.5
|  |  |  | Extrusion frame | 0.5
|  |  |  | Electrical panel cutout & mounting | 1
|  |  |  | Tank Assembly | 1
|  |  |  | Stirrer Assembly | 1
|  |  |  | Metering unit Assembly with report | 1.5
|  |  |  | Vacuum line Assembly | 1
|  |  |  | Pneumatic tubing and ferruling (Ducting & FRL mtg SV mtg) | 1
|  |  |  | Boom Assembly | 0.5
|  |  |  | Gun assly (TWIN gun assly & testing report) | 0.5
|  |  |  | Hose preparation | 0.5
|  |  |  | Flushing trolley assembly | 0.5
|  |  |  | Name plate, all legends (safety), acrylic cutting. | 0.5
|  |  | Electrical Assembly | Electrical layout, MP wiring, OP wiring | 4
|  |  |  | M/C wiring, I/O checking, labeling & parameter setting | 1
|  |  | Software Assembly | Machine PLC programming | 1
|  | Purchase | Reciept of Bought out items | Reciept of Bought out items | 56
|  |  | Reciept of Manufacturing items | Reciept of Manufacturing items | 21
|  | Testing | Internal machine trials | Internal machine trials ( Vacu.leak test,Temp. trial, ratio trials, Mixing trial,hardness report,etc) | 4
|  |  | Quality checking | Quality checking | 1
|  |  | Customer PDI | Customer PDI | 2
|  | Dispatch | Machine cleaning & dispatch activities | MOM completion | 1
|  |  |  | Machine cleaning & Dispatch activities | 4
MMD | INTELLO-AE - 1-9-PG-100-100-60-S-2H-SM | Design | Design activity | Study of PR sheet/ RFQ | 1
|  |  |  | Understanding machine + customer requirement | 1.5
|  |  |  | Preperation of DAP document + Machine calculations | 7
|  |  |  | DAP Submission + coordination/ customer meeting/ DAP visit | 1
|  |  |  | Customer Approval (Max) | 7
|  |  |  | Long Lead release | 2
|  |  |  | Updation on DAP points and detail designing | 4
|  |  |  | Integration of attachment modeling and Detail drafting | 5
|  |  |  | Release of documentation+ P&I + flowcharts,Process parameter sheet, etc. | 2
|  |  |  | Design Release through NAV | 0.5
|  |  |  | Design Support during PDI | 1
|  |  |  | MOM point clearance as per PDI | 2
|  |  |  | Manual Preperation | 3
|  | Production | Mechanical Assembly | MMD Base Frame Assembly | 0.5
|  |  |  | MMD Extrusion Frame Assembly | 0.5
|  |  |  | Electrical Panel Cutout & mounting | 1
|  |  |  | Tank Assembly | 2
|  |  |  | Stirrer Assembly | 1
|  |  |  | Metering Unit Assembly | 2
|  |  |  | Vacuum line Assembly | 1
|  |  |  | Pneumatic tubing & ferruling | 1
|  |  |  | FRL & SV valve mtg | 1
|  |  |  | Vacuum chamber assembly | 3.5
|  |  |  | Conveyour assembly | 2
|  |  |  | Robot mounting | 1
|  |  |  | Hose preparation | 1
|  |  |  | Ducting, pneumatic tubing & ferruling | 1
|  |  |  | Gun Assembly (Static/Dynamic) | 1
|  |  |  | Flush panel & Acrylic fitting. | 1
|  |  |  | Curtain sensor, job sensors mounting | 1
|  |  |  | Legends, name plate, safety stickers | 0.5
|  |  | Electrical Assembly | Electrical layout, MP wiring, OP wiring | 12
|  |  |  | M/C wiring, I/O checking, labeling & parameter setting | 12
|  |  | Software Assembly | Machine PLC programming | 2
|  |  |  | Robot teching & programming | 2
|  | Purchase | Reciept of Bought out items | Reciept of Bought out items | 56
|  |  | Reciept of Manufacturing items | Reciept of Manufacturing items | 21
|  | Testing | Internal machine trials | Internal machine trials ( Vacu.leak test,Temp. trial, ratio trials, Mixing trial,hardness report,etc) | 8
|  |  | Quality checking | Quality checking | 1
|  |  | Customer PDI | Customer PDI | 4
|  | Dispatch | Machine cleaning & dispatch activities | MOM completion | 4
|  |  |  | Machine cleaning & Dispatch activities | 8
MMD | INTELLO-ET-1.5-3.6-GG-45-10-I-1H-DM | Design | Design activity | Study of PR sheet/ RFQ | 1
|  |  |  | Understanding machine requirement | 1
|  |  |  | Preperation of DAP document + Machine calculations | 3
|  |  |  | DAP Submission + coordination/ customer meeting/ DAP visit | 0.5
|  |  |  | Customer Approval (Max) | 7
|  |  |  | Long Lead release | 1
|  |  |  | Updation on DAP points and detail designing/drafting | 2
|  |  |  | Design Release through NAV | 1
|  |  |  | Release of testing chart whenever required. | 1
|  |  |  | Design Support during on shopfloor | 0.5
|  |  |  | MOM point clearance as per PDI | 1
|  |  |  | Manual Preperation | 2
|  | Production | Mechanical Assembly | Base frame assembly | 0.5
|  |  |  | Melter assembly | 2
|  |  |  | Electical panel cutout & mounting | 1
|  |  |  | Tank assembly | 2
|  |  |  | Stirrer assembly | 1
|  |  |  | Metering unit assembly | 2
|  |  |  | FRL & SV mounting with extrusion frame assembly | 1.5
|  |  |  | Vacuum line assembly | 2
|  |  |  | Mixer assembly | 2
|  |  |  | Hose preparation | 1
|  |  |  | Ducting & pneumatic tubing | 2
|  |  |  | Flushing tank assembly | 0.5
|  |  |  | Legends, name plate, safety stickers,arrows | 0.5
|  |  | Electrical Assembly | Electrical layout, MP wiring, OP wiring | 6
|  |  |  | M/C wiring, I/O checking, labeling & parameter setting | 6
|  |  | Software Assembly | Machine PLC programming | 1
|  | Purchase | Reciept of Bought out items | Reciept of Bought out items | 56
|  |  | Reciept of Manufacturing items | Reciept of Manufacturing items | 21
|  | Testing | Internal machine trials | Internal machine trials ( Vacu.leak test,Temp. trial, ratio trials, Mixing trial,hardness report,etc) | 8
|  |  | Quality checking | Quality checking | 1
|  |  | Customer PDI | Customer PDI | 4
|  | Dispatch | Machine cleaning & dispatch activities | MOM completion | 2
|  |  |  | Machine cleaning & Dispatch activities | 6